## Design Test Plan
DESIGN TEST PLAN — RB-CTRL-04: KYC Documentation Review — Branch Network
Retail Banking ¦ FY2026 Q2 ¦ MetricStream ¦ ⚠ WEAK Rating — Training Gap 18 Months
Control ID | RB-CTRL-04
Last Training | October 2023 — 18 months ago
Regulatory Gap | FinCEN CDD Rule Q1 2024 update not incorporated in branch training or checklist
April Sampling Result | 4 incomplete files in 62 sampled (6.5% error rate) — 2 regulatory breaches
Overall Test Result | FAIL — P2 Action ACT-004: Branch refresher training (45 days)
Test Case ID | Scenario | Regulation Tested | Branch / Staff Profile | Document Collected | Expected Outcome | Actual Outcome | Result | Finding | Remediation
TC-01 | Individual customer onboarding — standard documentation | BSA/AML — standard CDD requirements | Branch: Manchester St / Staff: Hired Nov 2024 (post-training) | Passport + Proof of Address collected | All required documents collected and filed correctly | Pass: Documents complete. Correctly filed in CRM. | Pass | No finding | No remediation required
TC-02 | Business account — beneficial ownership under 25% threshold | FinCEN CDD Rule Q1 2024 — 25% beneficial ownership threshold | Branch: 5th Ave / Staff: Hired Jan 2025 | Beneficial ownership form completed using old 50% threshold criteria | All beneficial owners holding ≥25% must be documented per Q1 2024 CDD update | FAIL: Form collected only disclosed one owner at 51%. Two owners at 28% and 31% not documented. | Fail | Regulatory breach — FinCEN CDD Q1 2024 non-compliant. Two beneficial owners not documented. | ACT-004: (1) Updated checklist to be distributed within 15 days, (2) File to be remediated within 5 days, (3) All business accounts since Q1 2024 to be retrospectively reviewed
TC-03 | PEP identification and escalation | BSA/AML — Enhanced Due Diligence for PEPs | Branch: Downtown / Staff: Hired Jun 2023 (pre-training, experienced) | Standard ID + Source of funds declaration | PEP flagged in screening; automatic FIU escalation within 24 hours | Pass: PEP correctly identified via screening tool. FIU notified at T+00:18 (well within 24hrs). | Pass | No finding — experienced staff correctly handled PEP escalation | No remediation required
TC-04 | Periodic refresh — high-risk customer overdue | FinCEN CDD — risk-based refresh schedule | Branch: Westside / Customer: High-risk rating, annual refresh due Feb 2026 | Refresh overdue by 60 days as of Apr 2026 | CRM alert triggered; refresh initiated before April RCSA sampling | FAIL: Refresh not completed. CRM alert was sent but branch staff didn't action it. Account is 60 days overdue. | Fail | Operational failure — periodic refresh SLA breached for high-risk customer. | ACT-004: Refresh to be completed within 5 days. Branch manager to be briefed on CRM alert process.
TC-05 | Document authenticity — proof of address | BSA/AML — document verification standards | Branch: Eastside / Staff: Hired Mar 2024 | Utility bill submitted — date 4 months ago (outside 3-month requirement) | Outdated utility bill rejected; customer asked to provide current document | Pass: Outdated document correctly rejected. Customer contacted for current document. | Pass | No finding | No remediation required
TC-06 | Post-training validation (FUTURE TEST — after ACT-004 completion) | All BSA/AML, FinCEN CDD Q1 2024, OCC 2024 procedures | All branch staff — refresher training completion by 22-Jun-2026 | Knowledge assessment — 20-question test on updated procedures | ≥85% pass rate across all branch staff; updated checklist adoption confirmed | NOT RUN — pending training completion (ACT-004, due 22-Jun-2026) | Not Run | N/A — test to be run post-training | Training to be completed 22-Jun-2026. Re-test to follow within 5 business days.

## Monthly Sampling Results
KYC MONTHLY SAMPLING RESULTS — RB-CTRL-04 ¦ FY2026 YTD
Month | Transactions | Sample Size | Complete Files | Incomplete Files | Error Rate | Key Finding | Status
January 2026 | 4218 | 211 | 209 | 2 | 0.95% | 2 minor documentation gaps — source of funds declaration incomplete | Remediated
February 2026 | 3891 | 195 | 194 | 1 | 0.51% | 1 missing proof of address — customer contacted | Remediated
March 2026 | 4502 | 225 | 220 | 5 | 2.22% | 5 gaps — 2 business accounts, 3 individual (staff turnover impact) | Partially remediated
April 2026 | 4677 | 234 | 230 | 4 | 1.71% | 4 gaps — 2 FinCEN CDD breaches (regulatory breach), 2 operational gaps | In remediation — P2 Action