CONTROL PERFORMANCE EVALUATION KYC Documentation Review — Branch Network Retail Banking Division ¦ RB-CTRL-04

| Control ID | RB-CTRL-04 |
| --- | --- |
| Control Name | KYC Documentation Review — Branch Network |
| Business Division | Retail Banking Division |
| Document Type | Control Performance Evaluation |
| Prepared By | Risk & Controls Team |
| Review Date | 30-Apr-2026 |
| Classification | Confidential — Internal Use Only |
| GRC Reference | RCSA-2026-RB-Q2 ¦ ServiceNow / MetricStream |

Performance Summary

| KPI | Target | Actual (Apr 2026) | Status |
| --- | --- | --- | --- |
| KYC File Completeness Rate | 100% of sampled files | 93.5% (4 incomplete in 62) | Fail |
| FinCEN CDD Compliance Rate | 100% — beneficial ownership | 96.8% (2 beneficial ownership gaps) | Fail |
| PEP Escalation Timeliness | 100% within 24 hours | 100% (no PEPs in Apr sample) | Pass |
| Periodic Refresh Compliance | 95% of due refreshes completed | 88.2% (backlog from staff capacity) | Fail |
| Training Currency | All staff trained <12 months | 61.3% (staff hired since Oct 2023 untrained) | Fail |

Overall Rating: WEAK Four KPIs in breach — the most serious being the 2 direct FinCEN CDD compliance breaches on beneficial ownership documentation. The root cause (18-month training gap + outdated checklist) is clear and addressable. Actions: (1) Updated KYC checklist — 15 days, (2) Branch refresher training — 45 days, (3) Retrospective file review for all business accounts onboarded since Q1 2024. The control cannot be upgraded to ADEQUATE until two consecutive clean monthly sampling cycles are achieved following training completion.